## Slide 1
Software Engineering
CS-303
Slides by:
Rubab Jaffar
Lecture # 12,13
18 Feb
Work Breakdown Structure (WBS)

## Slide 2
SW
Project
SCOPE
Planning
Requirements
Design
Development
Testing
Built
Release
Deployment
UAT
Operation
Maintenance

## Slide 3: Project Management

## Slide 4: Why is it needed?

## Slide 5: Why (cont…)
Notes: A ballpark figure is a rough numerical estimate or approximation. Ballpark figures are commonly used by accountants, salespersons and other professionals toestimate current or future results

## Slide 6: Project Management Processes (Initiation)
Scope
(definition)
Initiation
Cost
(estimates, …)
WBS
Time
(activity diagrams, …)
Human Resources
(RACI matrix, …)
Also to consider: Quality, Risk, Communication, Procurement, Integration (PMBOK® knowledge areas)
Project Charter
Project Management Plan
Project Scope
Statement

## Slide 7: Introduction
Dividing complex projects to simpler and manageable tasks is the process identified as Work Breakdown Structure (WBS).
Usually, the project managers use this method for simplifying the project execution. In WBS, much larger tasks are broken-down to manageable chunks of work. These chunks can be easily supervised and estimated.
Work Package: A group of related tasks that are defined at the same level within a work breakdown structure.
7

## Slide 8: What is WBS?
According to the PMI’s Project Management Body of Knowledge (PMBOK), a work breakdown structure is “A hierarchical decomposition of the total scope of work to be carried out by the project team to accomplish the project objectives and create the required deliverables.”

## Slide 9: What is WBS?
A work breakdown structure element may be a product, data, a service, or any combination. A WBS also provides the necessary framework for detailed cost estimating and control along with providing guidance for schedule development and control
9

## Slide 12: The Work Breakdown Structure
Used as a basis for a number of in particular to produce the subsidiary plans of the Project Management Plan.
The WBS is a deliverable-oriented hierarchy of decomposed project components.
The WBS is a representation of the detailed project scope statement that specifies the work to be accomplished by the project.
The elements comprising the WBS assist the stakeholders in viewing the end product of the project.
The work at the lowest-level WBS component is estimated, scheduled, and tracked.
WBS

## Slide 13: When should we develop WBS?
Once the project Scope is agreed (finalized) then before starting the project we need to plan various components (activities) of software development project.

## Slide 14
Deliverable-Based Work Breakdown Structure
Phase-Based Work Breakdown Structure

## Slide 15: WBS Guidelines
Accurate and readable project organization.
Accurate assignment of responsibilities to the project team.
Indicates the project milestones and control points.
Helps to estimate the cost, time, and risk.
Illustrate the project scope, so the stakeholders can have a better understanding of the same.
15

## Slide 16: Guidelines - continued
Include three types of project work
  Product
    Specifically assigned to a physical product as a unique deliverable
    This subset is sometimes referred to as the product breakdown structure
  Integration
    When products are brought together as a unit
    Can be at any level
  Support
    Level of Effort, Administration, Expenses, Improvement Practices, Contractor Management

## Slide 17: Steps to build a WBS
Begin with the Charter, focusing on Objectives and Deliverables
Break the main product(s) down into sub-products
Set the structure to match how you’ll manage the project
Lowest level not too detailed, not too large
Is there a need for Integration?
Identify support activities
Check for completeness - is all the effort included?
Develop a coding structure if needed
Assign work package managers
17

## Slide 18: Construction of a WBS
Identifying the main deliverables of a project is the starting point for deriving a work breakdown structure.
This important step is usually done by the project managers and the subject matter experts (SMEs) involved in the project. Once this step is completed, the subject matter experts start breaking down the high-level tasks into smaller chunks of work.
In the process of breaking down the tasks, one can break them down into different levels of detail. One can detail a high level task into ten sub tasks while another can detail the same high level task into 20 sub tasks.
18

## Slide 19: WBS Formats
Work Breakdown Structure Chart
Hierarchical Structure
Tabular WBS Design

## Slide 20: Displaying the WBS Example of outlined WBS.
20

## Slide 21: Displaying the WBS Example of Chart WBS.
21

## Slide 22
https://online.visual-paradigm.com/diagrams/features/work-breakdown-structure-software/

## Slide 23: WBS helps manager
  Facilitates evaluation of cost, time, and technical performance of the organization on a project.
  Provides management with information appropriate to each organizational level.
  Helps organization to project responsibilities to organizational units and individuals
  Helps manager plan, schedule, and budget.
  Defines communication channels and assists in coordinating the various project elements.
23

## Slide 24: Pitfalls
There are common pitfalls to creating a WBS. If you can keep these few possible, you and your team will be much more successful at creating a useful and accurate Work Breakdown Structure.
Level of Work Package Detail
Deliverables Not Activities or Tasks
WBS is not a Plan or Schedule
WBS Updates Require Change Control
WBS is not an Organizational Hierarchy
24

## Slide 25: The Dictionary of the WBS
WBS
A WBS dictionary is a companion document to the WBS that describes each WBS element. For each WBS element, the WBS dictionary includes a statement of work, a list of associated activities, and a list of milestones.
Other information can include the responsible organisation, start and end dates, resources required.

## Slide 26: A Full WBS Structure
26

## Slide 27: WBS Guidelines
27

## Slide 28: WBS Guidelines
28

## Slide 29: Suggested WBS Template Process

## Slide 30: WBS Project Work
30

## Slide 31: WBS Template
Component groups with a ‘+’ in front of them are ‘rolled up’ – subcomponents are hidden to reduce clutter
31

## Slide 32: WBS Check List
Does it define 100% of the work that will be produced by the project?
Does it use a coding structure so that each element has a unique ID that shows its place in the hierarchy e.g. 1.1, 1.2, 1.1.1, 1.1.2?
Will project stakeholders be able to understand the project scope from the WBS?
Does each level represent 100% of the work required to deliver the parent level?
Is the decomposition sufficient that the tasks required to deliver each work package can easily be identified?
Is it in the format that gives a clear graphical, textual or tabular breakdown of the project scope?
32

## Slide 33: WBS Check List
Does it have a least two levels with at least one level of decomposition?
Was it created by those who will be performing the work?
Is it being regularly updated as project changes are approved?
Can you identify one person who is accountable for each work package?
Can you clearly define the acceptance criteria for each work package?
Does it allow you to estimate costs accurately?
Does the WBS have logical summary elements that can be used in tracking progress and performance?
33

## Slide 34: Example WBS
Redecorate Room
  Prepare materials
    Buy paint
    Buy a ladder
    Buy brushes/rollers
    Buy wallpaper remover
  Prepare room
    Remove old wallpaper
    Remove detachable decorations
    Cover floor with old newspapers
    Cover electrical outlets/switches with tape
    Cover furniture with sheets
  Paint the room
  Clean up the room
    Dispose or store left over paint
    Clean brushes/rollers
    Dispose of old newspapers
    Remove covers
WBS

## Slide 35: References
https://itpmschool.com/work-breakdown-structure-guide/
https://itsadeliverything.com/got-a-wbs-for-your-agile-project-sure-of-course

## Slide 36
That is all
36